## Slide 1
Stages of Front-end Loading
FEL Stage | FEL-1 | FEL-2 | FEL-3 | FEL-4 | FEL-5
 | Business Assessment | Conceptual Engineering (pre-FEED) | Basic Engineering (FEED) | Detailed Engineering | Commissioning
 |  | Alternative Evaluation/Selection | Scope definition | EPCM | Operation, IQ/OQ, Training
Purpose |  |  |  |  | 
 | Identify project aligned | Select preferred process/technology options | Complete scope definition, validate | Implement PEP | Meet design nameplate and
 | with business objectives |  | business premises, ensure execution |  | Evaluate against business objective
 |  |  | with a degree of certainty. |  | 
Objectives |  |  |  |  | 
 | Define business premises | Validate business premises | Finalize scope, schedule and cost | Complete detailed engineering | Validate & Qualify
 | Define business objectives | Analyze options and select best alternative | PEP (Project Execution Plan) | Obtain required permits | Achieve nameplate production
 | List techno-commercial | Develop process scope of work, PFD, etc. | Mitigation of risk & uncertainties | Create equipment procurement plan | Train O&M personnel
 | assumptions | Utilities analysis, gap analysis, etc. | Define/gather project team | Mobilize construction resources | Complete trial run
 | Identify risks, mitigants | Identify uncertainties and risks | Secure project funding |  | 
 | Preliminary economics |  |  |  | 
Deliverables |  |  |  |  | 
 | FEL-1 deliverable check-list | FEL-2 deliverable check-list | FEL-3 check-list | Purchase and receive equipment, etc. | Operate and collect data
 | Abstract/Objective Stmt. | Basic economic model | Major equipment list, specs, quotes | Manage construction per PEP | Optimize
 | Assign resources : | PFD, basic layout/plot plan, etc. | Finalize plot plan | Manage change orders | Project closure
 | Project Manager | Permitting requirements and strategy | Issue for design, P&ID, controls, etc. | Final HAZOP review | 
 | Project Engineer | O&M strategy | Conduct HAZOP review, EHS strategy | Commission project | 
 | Other | EHS requirements and strategy | PEP with work breakdown structure |  | 
 |  | Technical risk assessment | and sub-contracting plan |  | 
 |  | Major equipment list and key vendors |  |  | 
 | CAPEX and O&M ±50% | CAPEX & O&M ±30% | CAPEX ±10%; O&M ±15% |  | 
 | FEL-2 Plan with milestones | FEL-3 Plan with milestones | Detailed construction schedule |  | 
Costs | < $10,000 | 0.33% --TIC – 1% | 1% -- TIC – 3% | 5% -- Engineering – 15% +/- | From O&M budget
 |  |  |  | (rest for Procurement & Construction) | 
Duration | < 1 to ~2 weeks | 2 to 12 weeks | 6 to 18 weeks | 6 to 24 months | 
 | We can provide this | service . |  |  |